## Inputs
Inputs - every number used by the model
Blue cells are inputs; change them and every sheet recalculates. Green = DATA from 03, blue tint = BENCHMARK from 02b, yellow = ASSUMPTION (needs Finance or business confirmation). Single-value rows copy the Base value into Low and High. All money in USD.
Key | Input | Low | Base | High | Unit | Type | Source / note
A. Internal baseline (TTM 2025-10-22 to 2026-10-21)
rev_gross | GCC gross revenue, incl VAT |  | 13390000 |  | USD/yr | DATA | 03-baseline-metrics.md, summary table, GCC total
rev_soft | Softline gross revenue, incl VAT |  | 8460000 |  | USD/yr | DATA | 03-baseline-metrics.md, summary table, softline total (9 brands)
rev_hard | Hardline gross revenue, incl VAT |  | 4930000 |  | USD/yr | DATA | 03-baseline-metrics.md, summary table, hardline total (9 brands)
rev_net | GCC net revenue after cancellations and returns, incl VAT |  | 12040000 |  | USD/yr | DATA | 03-baseline-metrics.md, summary table, GCC total net
rev_soft_net | Softline net revenue, incl VAT |  | 7140000 |  | USD/yr | DATA | 03-baseline-metrics.md, summary table, softline net
ret_rate | Cancellation plus return rate (value) = 1 - net/gross |  |  |  | % | DATA | Derived from the two rows above
stock_asp | Stock on hand, valued at selling price incl VAT |  | 6480000 |  | USD | DATA | 03-baseline-metrics.md, summary table (all unified_inventory sources)
stock_units | Stock on hand, units |  | 155074 |  | units | DATA | 03-baseline-metrics.md, summary table
st_90d | Sell-through, last 90 days (GCC) |  | 40% |  | % | DATA | 03-baseline-metrics.md, summary table
aged180 | Stock value over 180 days since receipt (upper bound proxy) |  | 2690000 |  | USD | DATA | 03-baseline-metrics.md, ageing table, GCC total; caveat 5 says upper bound
lost_daily | Stock-out proxy, softline demand on zero-stock SKU-locations (upper bound) |  | 6666 |  | USD/day | DATA | 03-baseline-metrics.md, stock and stock-out table, softline total
lost_anchor | Stock-out proxy, lower anchor (locations selling 0.2+ units a day) |  | 1376 |  | USD/day | DATA | 03-baseline-metrics.md, split of stock-out proxy (query R1b)
sizefit | Namshi size or fit returns, at listing price |  | 682000 |  | USD/yr | DATA | 03-baseline-metrics.md, returns section (DD9 method)
g_soft | Softline unit growth, last 6 months vs previous 6 |  | 25% |  | % | DATA | 03-baseline-metrics.md, summary table; includes launches
g_gcc | GCC unit growth, last 6 months vs previous 6 |  | 49% |  | % | DATA | 03-baseline-metrics.md, summary table; includes brand launches and new channels
g_uspa | U.S. Polo Assn. unit growth, last 6 months vs previous 6 (closest to like-for-like) |  | -1% |  | % | DATA | 03-baseline-metrics.md, summary table
B. Financial assumptions
vat | Blended VAT rate in gross revenue (UAE 5%, KSA 15%) |  | 10% |  | % | ASSUMPTION | Country mix not in 03; about half KSA assumed. Gross is incl VAT (03 definitions)
gm | Gross margin, % of net revenue ex VAT (price minus landed cost) | 35% | 40% | 45% | % | ASSUMPTION | Brand distributor on marketplaces; no unit cost usable in the warehouse (03 caveat 6). Finance to confirm
var_cost | Variable selling cost on extra sales (marketplace commission share, fulfilment), % of net ex VAT |  | 15% |  | % | ASSUMPTION | Conservative; recovered sales valued at gross margin less this
coc | Cost of capital, used to value cash tied in stock | 10% | 12% | 15% | %/yr | ASSUMPTION | Typical GCC/India mid-size company WACC; Finance to confirm
dr | Discount rate for NPV |  | 12% |  | %/yr | ASSUMPTION | Set equal to cost of capital base
md_pct | Markdown and ageing write-down cost borne by Opptra, % of net revenue ex VAT | 6% | 10% | 15% | % | ASSUMPTION | 02b B3 illustrates 15-25% of gross sales and 05 uses 20%; kept lower because marketplaces fund part of promotions. Cross-check: aged stock row on Levers
clear_disc | Clearance discount on stock over 180 days (cross-check only) |  | 40% |  | % | ASSUMPTION | Used only to sanity-check md_pct
ret_handling | Cost of handling one returned USD (reverse logistics, marketplace return fees, damage) |  | 15% |  | % | ASSUMPTION | No GCC figure in 02b A5; Finance to confirm from Namshi settlement reports
keep_share | Share of avoided size returns that become kept sales |  | 50% |  | % | ASSUMPTION | Rest are orders that simply do not happen
hard_factor | Hardline stock-out intensity vs softline (per USD of revenue) |  | 0.5 |  | x | ASSUMPTION | Replen run covers softline only (03 caveat 9); hardline has few SKUs and 48% sell-through, so assumed half
planners | People doing forecasting and buy planning (FTE) |  | 4 |  | FTE | ASSUMPTION | Ashish, Mahesh plus buyers/brand managers (06 section 4)
planner_cost | Loaded cost per planner, GCC |  | 55000 |  | USD/yr | ASSUMPTION | 05 section 4.1, GCC planning analyst loaded rate
manual_share | Share of planner time spent on manual forecasting and spreadsheet buy plans |  | 30% |  | % | ASSUMPTION | Not measured; check in Phase 0
new_share | Share of softline revenue from styles in their first season |  | 30% |  | % | ASSUMPTION | 03 new-styles table shows steady new-style drops; not measured as revenue
uplift_pt | Revenue uplift on new styles per hit-rate point |  | 1% |  | %/pt | ASSUMPTION | 1 point more hits = 1% more new-style revenue
growth_cap | Cap on annual growth used in Growth sheet |  | 10% |  | %/yr | ASSUMPTION | Conservative cap; observed unit growth is mostly launches (03 caveat 2)
cost_mult | Cost multiplier on 05 Option D cost | 1.22 | 1 | 1 | x | ASSUMPTION | Low = top of 05 range (USD 832k / 680k); high case does not assume cheaper delivery
ramp1 | Adoption / realisation, year 1 (pilot first) | 25% | 30% | 40% | % | ASSUMPTION | 05 section 5 ramp 30/70/100; pilot Dec 2026 - Apr 2027 on 3 brands (06 section 11)
ramp2 | Adoption / realisation, year 2 | 55% | 70% | 85% | % | ASSUMPTION | 05 section 5
ramp3 | Adoption / realisation, year 3 | 85% | 100% | 100% | % | ASSUMPTION | 05 section 5
haircut | Overlap haircut on levers a+b+c (stock-outs and inventory trade off) | 30% | 20% | 10% | % | ASSUMPTION | 02b B2 point 5: do not add all levers together
p_gate1 | Probability the pilot passes Gate 1 (stage-gated scenario) |  | 50% |  | % | ASSUMPTION | No track record; 06 section 11 hold/stop rule. Used only in the stage-gated block
pilot_ben | Benefit counted during Phases 0-1 (stage-gated scenario) |  | 0 |  | USD | ASSUMPTION | Set to zero: pilot covers 3 brands and is for proof, not value
C. Lever ranges (relative change vs today unless 'points')
fe_red | Forecast error (WMAPE) reduction - pilot KPI, not valued directly | 10% | 20% | 30% | % | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 (McKinsey 20-50%, academic 19-26%)
ls_red | Lost sales from stock-outs, reduction | 10% | 20% | 30% | % | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 (McKinsey fashion 15-25%, vendor 13-28%)
realisable | Share of the stock-out proxy that is real lost demand |  | 40% | 60% | % | ASSUMPTION | Low = 03 lower anchor / upper bound; 63% of proxy has stock elsewhere (03)
sales_lift | Cap: total sales lift from better buying and allocation | 1% | 3% | 5% | % | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 (Zara field experiment 3-4%)
inv_red | Inventory held at same availability, reduction | 5% | 10% | 15% | % | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 (McKinsey State of Fashion 5-15%)
md_red | Markdown and write-down cost, reduction | 5% | 10% | 20% | % | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 (BCG up to 2 pts margin; vendor -2% markdown loss)
st_pts | Sell-through, points - cross-check and pilot KPI, not valued directly | 1 | 3 | 5 | pts | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 (GCC case +1.6, Guess +5)
sf_red | Size or fit returns, reduction (size curves in buys) | 0% | 3% | 7% | % | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 return-rate row; 06 section 15 target -3%
time_saved | Planner manual-work time saved | 15% | 25% | 40% | % | ASSUMPTION | No benchmark in 02b; capacity value, not a headcount cut
npd_pts | NPD hit rate, points (UPSIDE ONLY, excluded from base) | 0 | 5 | 10 | pts | BENCHMARK | 02b-gcc-context-and-benchmarks.md B3 (no published evidence; option value)

## Levers
Levers - how each benefit is calculated (Low / Base / High)
Every cell is a formula on Inputs and Costs. Annual benefit = steady state at full adoption on today's revenue. One-off cash release and NPD upside (f) are shown but never added to the annual benefit.
Step | Low | Base | High | How
Common
VAT divisor (1 + VAT) |  |  |  | Strips VAT from gross numbers
Net revenue ex VAT
Contribution margin on extra sales |  |  |  | Gross margin less variable selling cost
(a) Recovered lost sales from fewer stock-outs
Softline lost demand a year (gross) |  |  |  | Stock-out proxy x 365 x realisable share
Hardline lost demand a year (gross) |  |  |  | Softline intensity x hardline revenue x hardline factor
Total lost demand a year (gross)
Recovered sales before cap |  |  |  | Pool x lost-sales reduction
Cap: revenue x total sales lift |  |  |  | 02b sales-lift ceiling
Recovered gross sales (lower of the two)
(a) Value: recovered sales at contribution margin |  |  |  | Ex VAT, net of returns, x contribution
(b) Working capital released from lower inventory
Stock at cost, ex VAT |  |  |  | Selling-price value -> cost
One-off cash release at full adoption (shown separately) |  |  |  | NOT in annual benefit
(b) Value: annual carrying saving on released cash |  |  |  | Cash release x cost of capital
(c) Markdown and ageing write-down avoided
Markdown and write-down cost a year |  |  |  | Net ex VAT x markdown share
Cross-check: stock over 180 days x clearance discount, ex VAT |  |  |  | Should be the same order as the row above
(c) Value: markdown and write-down avoided
(d) Size-curve improvement: fewer size or fit returns
Size or fit returns a year, ex VAT |  |  |  | USD 682k base
(d) Value: handling cost avoided plus margin on kept sales
(e) Planner time saved
(e) Value: planner capacity freed |  |  |  | Capacity, not a headcount cut
Total annual benefit (steady state, current revenue base)
Sum of levers a to e
Less overlap haircut on a+b+c |  |  |  | 02b B2: levers trade off
ANNUAL BENEFIT at full adoption |  |  |  | Excludes NPD (f) and one-off cash
(f) NPD upside - shown separately, EXCLUDED from all totals
(f) NPD hit-rate upside a year |  |  |  | Upside only
Cross-check against the sell-through benchmark
Units sold in 90 days implied by today's sell-through
Sell-through after recovered sales and lower stock
Implied sell-through change, points (02b benchmark in Inputs st_pts) |  |  |  | Should sit near the benchmark
Three-year view (ramp-up applied)
Benefit Y1
Benefit Y2
Benefit Y3
Cost Y1 |  |  |  | Costs sheet x multiplier
Cost Y2
Cost Y3
Net Y1
Net Y2
Net Y3
PV of benefits |  |  |  | Year-end discounting
PV of costs
3-YEAR NPV (excl one-off cash release)
ROI multiple (PV benefits / PV costs)
Cash release Y1 |  |  |  | Follows adoption
Cash release Y2
Cash release Y3
3-year NPV incl one-off cash release

## Costs
Costs - Option D (hybrid, staged), from 05-build-vs-buy.md section 4.5
Rates and months are inputs (blue). They rebuild 05's totals (USD 191.6k / 238.4k / 250.2k = 680.2k). Year 1 = Nov 2026 - Oct 2027. Phase dates from 06 section 11. Business time is not in 05; it is added below as an ASSUMPTION so the ROI is not flattered. Scenario cost multiplier is on Inputs.
Phase | People cost rate (USD/yr) | GCP (USD/month) | Data and licences (USD/month) | One-off (USD) | Months in Y1 | Months in Y2 | Months in Y3 | Source
Phase 0 - Prove the basics (9 Nov - 18 Dec 2026) | 97000 | 200 | 0 | 500 | 1.5 | 0 | 0 | 05 4.5 FTE table; one-off = capped Cardio Bunny scrape
Phase 1 - Pilot, 3 brands, Ramadan 2027 (21 Dec 2026 - 30 Apr 2027) | 151500 | 300 | 1000 | 0 | 4.5 | 0 | 0 | 05 4.5
Phase 2 - Scale to all brands (May - Dec 2027) | 202000 | 500 | 2000 | 0 | 6 | 2 | 0 | 05 4.5
Phase 3 - Own product (from Jan 2028; Y3 incl 0.5 partner success) | 208500 | 600 | 2000 | 0 | 0 | 10 | 0 | 05 4.5
Phase 3 - year 3 rate | 219000 | 600 | 2000 | 0 | 0 | 0 | 12 | 05 4.5 (219.0k incl partner success)
Business time not costed in 05 (ASSUMPTION)
Hours a week (Ashish, Mahesh 2-3 h each; Nitin 2 h; 3 pilot brand managers 2 h each; 06 section 12) | 12
Working weeks a year | 46
Loaded hourly cost, GCC staff (USD 55k / 1,840 h, 05 4.1 analyst rate)
Include business time in ROI cost? (1 = yes, 0 = no) | 1
Cost by year, per phase (USD)
Line | Y1 | Y2 | Y3 | 3 years
Phase 0 - Prove the basics (9 Nov - 18 Dec 2026)
Phase 1 - Pilot, 3 brands, Ramadan 2027 (21 Dec 2026 - 30 Apr 2027)
Phase 2 - Scale to all brands (May - Dec 2027)
Phase 3 - Own product (from Jan 2028; Y3 incl 0.5 partner success)
Phase 3 - year 3 rate
Subtotal, 05 Option D
Check against 05 (USD 191.6k / 238.4k / 250.2k / 680.2k) | 191600 | 238400 | 250200 | 680200
Business time (ASSUMPTION, added)
Total cost used in ROI (before scenario multiplier)
Same cost by type (USD)
Line | Y1 | Y2 | Y3 | 3 years
People
GCP
Data and licences
Business time

## Scenarios
Scenarios - low / base / high
Low uses every low input at once (and costs at the top of 05's range), so it is a stress case, not a likely case. Payback counts months from 9 Nov 2026 until cumulative benefit minus cost turns positive.
Result | Low | Base | High
Annual benefit, full adoption (current revenue base)
of which (a) recovered lost sales
of which (b) carrying saving on released stock
of which (c) markdown and write-down avoided
of which (d) fewer size or fit returns
of which (e) planner time
less overlap haircut
Benefit Y1 (pilot year, ramp applied)
Benefit Y2
Benefit Y3
Cost Y1
Cost Y2
Cost Y3
3-year NPV, excl one-off cash release
ROI multiple (PV benefits / PV costs)
One-off cash released from stock (full adoption)
3-year NPV incl one-off cash release
NPD upside a year (excluded above)
3-year benefit / 3-year cost, undiscounted
Payback month, excl cash release (months from start)
Payback month, incl cash release
Annual benefit needed at full adoption for NPV = 0 (break-even)
Stage-gated scenario (base inputs): leadership funds only Phases 0-1 until Gate 1 is met
Phase 0 cost (05)
Phase 1 cost (05)
Business time during Phases 0-1 (6 of 12 months, ASSUMPTION)
CASH AT RISK before the Gate 1 go / no-go
Benefit counted before Gate 1 (Inputs pilot_ben)
NPV if Gate 1 fails and work stops (spent in year 1)
NPV if Gate 1 passes and Phases 2-3 go ahead (= base NPV)
Probability Gate 1 passes (Inputs p_gate1)
Expected NPV, stage-gated
Expected NPV if all 3 years were funded up front (no stop option; a failed product still costs all 3 years)
Value of stage-gating (difference)
Monthly schedule (annual figures spread evenly within each year)
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Low: net a month
Low: cumulative
Low: month if positive
Low: net a month incl cash
Low: cumulative incl cash
Low: month if positive incl cash
Base: net a month
Base: cumulative
Base: month if positive
Base: net a month incl cash
Base: cumulative incl cash
Base: month if positive incl cash
High: net a month
High: cumulative
High: month if positive
High: net a month incl cash
High: cumulative incl cash
High: month if positive incl cash

## Growth
Growth - benefit on today's revenue vs a grown revenue base
Revenue-linked levers (a, b, c, d and the haircut) grow with revenue; planner time (e) does not. Growth rate = the lower of observed softline unit growth (03) and the cap on Inputs. Year 1 stays on today's base (conservative), so year n uses (1+g)^(n-1). Costs are the same in both views.
Observed softline unit growth (03)
Cap (Inputs)
Growth rate used
Note: GCC unit growth (+49%) and USPA like-for-like (-1%) are on Inputs; the cap keeps launches out.
Line | Low | Base | High
Benefit Y1, current base
Benefit Y2, current base
Benefit Y3, current base
Benefit Y1, grown base
Benefit Y2, grown base
Benefit Y3, grown base
3-year NPV, current base
3-year NPV, grown base
ROI multiple, grown base
Annual benefit at full adoption in Y3, grown base

## Sensitivity
Sensitivity - tornado on 3-year NPV (one driver at a time, others at base)
Each driver is moved to its Low and High input while all others stay at Base. Rows are ordered by swing at build time; the Rank column recalculates if inputs change. The top 5 are the drivers to test in the pilot. The calculation block below repeats the full Levers chain for every run.
Driver | Low input | High input | NPV at low input | NPV at high input | Base NPV | Swing (abs) | Rank | Top 5?
Markdown reduction (md_red)
Cost multiplier
Markdown cost share (md_pct)
Adoption ramp Y1-Y3
Lost-sales reduction (ls_red)
Overlap haircut
Realisable share of stock-out proxy
Inventory reduction (inv_red)
Sales-lift cap
Planner time saved
Cost of capital (coc)
Size or fit return reduction
Gross margin (gm)
Ramp row: Y1/Y2/Y3 move together; inputs shown are Y1.
Calculation block (one column per run)
| Markdown reduction (md_red) - low | Markdown reduction (md_red) - high | Cost multiplier - low | Cost multiplier - high | Markdown cost share (md_pct) - low | Markdown cost share (md_pct) - high | Adoption ramp Y1-Y3 - low | Adoption ramp Y1-Y3 - high | Lost-sales reduction (ls_red) - low | Lost-sales reduction (ls_red) - high | Overlap haircut - low | Overlap haircut - high | Realisable share of stock-out proxy - low | Realisable share of stock-out proxy - high | Inventory reduction (inv_red) - low | Inventory reduction (inv_red) - high | Sales-lift cap - low | Sales-lift cap - high | Planner time saved - low | Planner time saved - high | Cost of capital (coc) - low | Cost of capital (coc) - high | Size or fit return reduction - low | Size or fit return reduction - high | Gross margin (gm) - low | Gross margin (gm) - high
Common
VAT divisor (1 + VAT)
Net revenue ex VAT
Contribution margin on extra sales
(a) Recovered lost sales from fewer stock-outs
Softline lost demand a year (gross)
Hardline lost demand a year (gross)
Total lost demand a year (gross)
Recovered sales before cap
Cap: revenue x total sales lift
Recovered gross sales (lower of the two)
(a) Value: recovered sales at contribution margin
(b) Working capital released from lower inventory
Stock at cost, ex VAT
One-off cash release at full adoption (shown separately)
(b) Value: annual carrying saving on released cash
(c) Markdown and ageing write-down avoided
Markdown and write-down cost a year
Cross-check: stock over 180 days x clearance discount, ex VAT
(c) Value: markdown and write-down avoided
(d) Size-curve improvement: fewer size or fit returns
Size or fit returns a year, ex VAT
(d) Value: handling cost avoided plus margin on kept sales
(e) Planner time saved
(e) Value: planner capacity freed
Total annual benefit (steady state, current revenue base)
Sum of levers a to e
Less overlap haircut on a+b+c
ANNUAL BENEFIT at full adoption
(f) NPD upside - shown separately, EXCLUDED from all totals
(f) NPD hit-rate upside a year
Cross-check against the sell-through benchmark
Units sold in 90 days implied by today's sell-through
Sell-through after recovered sales and lower stock
Implied sell-through change, points (02b benchmark in Inputs st_pts)
Three-year view (ramp-up applied)
Benefit Y1
Benefit Y2
Benefit Y3
Cost Y1
Cost Y2
Cost Y3
Net Y1
Net Y2
Net Y3
PV of benefits
PV of costs
3-YEAR NPV (excl one-off cash release)
ROI multiple (PV benefits / PV costs)
Cash release Y1
Cash release Y2
Cash release Y3
3-year NPV incl one-off cash release

## Per-brand
Per-brand view - base-case annual benefit at full adoption, split by brand
Brand data (blue) from 03 summary and stock-out tables. Split keys: (a) softline by stock-out proxy USD/day, hardline by gross revenue; (b) by stock value; (c) by net revenue; (d) by Namshi size or fit returns; (e) by gross revenue. The overlap haircut is applied per brand. Totals tie to Levers base.
Brand | Segment | Gross USD (03) | Net USD (03) | Stock at ASP (03) | Stock-out proxy USD/day (03) | Size/fit returns USD (03) | (a) | (b) | (c) | (d) | (e) | Overlap | Total benefit | Share of total | Benefit % of brand gross
U.S. Polo Assn. | Soft | 6120000 | 5320000 | 1650000 | 3276 | 388000
French Connection | Soft | 681000 | 467000 | 789000 | 879 | 127000
Campus | Soft | 668000 | 542000 | 430000 | 786 | 68000
Penti | Soft | 403000 | 363000 | 343000 | 545 | 19000
Keds | Soft | 138000 | 96000 | 500000 | 336 | 30000
Vero Moda | Soft | 138000 | 89000 | 197000 | 217 | 24000
Puma | Soft | 109000 | 99000 | 154000 | 400 | 0
Nautica | Soft | 108000 | 86000 | 2000 | 54 | 14000
Cardio Bunny | Soft | 93000 | 72000 | 161000 | 172 | 14000
Nutricook | Hard | 1870000 | 1870000 | 534000 | 0 | 0
GTPlayer | Hard | 1520000 | 1510000 | 278000 | 0 | 0
NutriBullet | Hard | 574000 | 574000 | 353000 | 0 | 0
Carote | Hard | 572000 | 557000 | 644000 | 0 | 0
Bergner | Hard | 259000 | 255000 | 333000 | 0 | 0
Dowinx | Hard | 108000 | 108000 | 0 | 0 | 0
Tower | Hard | 17000 | 17000 | 51000 | 0 | 0
Qubo | Hard | 8000 | 8000 | 47000 | 0 | 0
Nuwey | Hard | 2000 | 2000 | 7000 | 0 | 0
Total
Check: Levers base annual benefit
Summary
U.S. Polo Assn.
Other softline brands (excl Cardio Bunny)
Cardio Bunny
Hardline brands
Stock-out proxy is softline only (03 caveat 9); Puma has no Namshi size/fit figure (n/a in 03), set to 0.